## Timeline
Institutional Review timeline summary Example Date | 2022-12-06
No
KEY ACTIVITIES | 18 weeks + Before planned event | 16+ weeks before | 14+ weeks before | 12+ weeks before | 10+ weeks before | 8+ weeks before | 6 wks + before event | 5 wks before | 4 weeks before | 3 weeks before | 2 weeks before | -1 week before | EVENT | + 1 wk | + 2 wks | + 3 wks | + 4 wks | 5 wks + after event
| 2022-08-02 | 2022-08-16 | 2022-08-30 | 2022-09-13 | 2022-09-27 | 2022-10-11 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2022-12-20 | 2022-12-27 | 2023-01-03 | 2023-01-10
Preparing for the Institutional Review Event
UEA and partner agree date of IR event | 2022-08-02: UEA/ PI
UEA holds meeting to identify Review Themes | 2022-08-30: UEA
UEA confirms Review Themes to partner | 2022-08-30: UEA
Partner prepares Institutional Review Submission | bar: 2022-09-13 to 2022-11-15
UEA conducts due diligence update, including previous years' accounts from partner, internet search, etc. | 2022-10-11: UEA; 2022-10-25: UEA
UEA approaches and confirms internal Panel member(s) | 2022-10-11: UEA; 2022-10-25: UEA
UEA confirms and approves Panel members including UEA representatives | 2022-10-25: UEA
Partner event admin: book and confirm room(s) | bar: 2022-10-25
UEA produces Institutional Review event agenda | 2022-11-01: UEA
Partner arranges senior staff, student and employer rep meetings | bar: 2022-11-01
UEA arranges accommodation for UEA Panel member(s) if required | 2022-11-08: UEA
Partner provides written Submission to UEA panel members | bar: 2022-11-22
Partner event admin: confirm dietary requirements and book refreshments | bar: 2022-11-22
Partner event admin: arrange parking for Panel members | bar: 2022-11-29
Partner event admin: prepare nameplates for all attendees | bar: 2022-11-29
Institutional Review Event and after
Panel's draft Conditions, Requirements and/or Recommendations shared at event | 2022-12-06: UEA
UEA circulates confirmed Conditions, Requirements and/or Recommendations as agreed by Chair | 2022-12-13: UEA
UEA drafts Institutional Review report | 2022-12-13: UEA; 2022-12-20: UEA
Partner recieves final report from UEA | 2022-12-27: UEA
Partner works on Conditions, Requirements and/or Recommendations and responds by agreed deadline | bar: 2022-12-13 to 2023-01-03
UEA signs off Conditions and/or Requirements | 2023-01-03: UEA
Recommendation of Panel considered at next meeting of UEA Senate | 2023-01-10: UEA