## Q1
FOI_26-233 Appendix A
| Item No. | Status | Project Name | One Line Description | Approved/ Estimated Budget | Planned Start Date | Planned End Date | Job Title of Officer responsible for delivery
| 1 | Live | ECB Floor 1 Refit - Teaching and Simulation Spaces | Address urgent and unplanned teaching space IT reconfiguration arising from essential building works to connect old/new parts of the Edith Cavell Building | No dedicated IT budget | 2026-02-13 | 2026-11-20 | Digital Project Manager
| 2 | Live | Improved Access-Auth for UEA Partners | Providing access to digital LIB resources for students at partner sites, supporting collaboration with UK/international institutions. On hold from 9 Feb 2026 - Current data inefficiences - ITCS taking forward direct via SPOT update Programme, Requester in agreement | On hold - no budget agreed | 2026-01-05 | N/a | Digital Project Manager
| 3 | Live | Data Centre Switch Replacement | Install hardware to efficiently "switch" massive data volumes between servers, storage/other devices, with UEAs Data Centre | 2026/27 £314,489 2027/28 £314,489 | 2025-01-30 | 2027-02-26 | Digital Project Manager
| 4 | Live | Network Control Core Switches and Automation Servers | Deliver a UEA network refresh, improving the controlled access of core data switches and linked authentications | 2026/27 £167,687 2027/28 £167,687 | 2025-01-30 | 2026-09-30 | Digital Project Manager
| 5 | Live | UERP GrantsNow Implementation | Move from current solution used for research costing and pricing, within UERP (ceases support Dec 2026) to a new partner solution "GrantsNow" | 2026/27 £63,954 2027/28 £66,513 | 2025-03-27 | 2026-10-31 | Digital Project Manager
| 6 | Live | CDP Phase 1 – Building 3 Refurb (ITCS) | Delivery of core IT Networking, Audio Visual and technical requirements, within Building 3 strip-out/refurbishment | 2026/27 £180,325 2027/28 £180,325 | 2024-05-10 | 2027-04-30 | Digital Project Manager
| 7 | Live | Curriculum Management System | New system to improve Course Management/workflows, Map Learing Outcomes/Employability attributes and provide improved Publication functionality. On hold from 16 Feb 2026 - Procurement impasse, as funding not in place for Akari software to be brought in. ITCS/FPG to advise at point of resurrection for the IT element of Project (Business level activity continues) | On hold - no budget agreed | 2022-07-01 | N/a | Digital Project Manager
| 8 | Live | MRI Evolution Cloud Hosting | EST Management System request: Deliver cloud-based Facilities Management system, providing dynamic functionality and integrations across UEA systems | 2026/7 = £82735.20 2027/8 = £70974.00 | 2026-08-18 | 2027-05-31 | Digital Project Manager
| 9 | Live | Service Management platform to enable unified campus services | Replacement of the Cherwell Service Management/Ticketing tool, delivering stronger workflow management, automation, integration and reporting | 2026/27 £64,075 2027/28 £64,075 | 2025-01-27 | 2026-10-14 | Digital Project Manager
| 10 | Live | Unstructured Data Migration | Through a joined-up RoadMap, address absence of effective data classification, retention and archiving practices across UEA within a managed migration. Defeat financial and GDPR risks, in advance of Microsoft's 2027 charging model increase for data storage (OneDrive) | No budget | 2026-02-02 | 2027-12-31 | Digital Project Manager
| 11 | Live | Migrate Apple Device Management to Intune | Switch our cloud hosting of Apple devices (Mac, iPad, iPhone) to "InTune" at nil additional cost, delivering better management, integration and maintenance capability | Nil. | 2025-10-29 | 2026-09-30 | Digital Project Manager
| 12 | Live | Secure Gateway for the Inflaim/Hiverge.AI Collaboration | CMP-submitted proposal. Provide a secure/automated technical pathway, for improved Research collaboration between the Inflaim project (RIN Number R211430) and our external partner, Hiverge.ai | Information not held - s.1(1)(a) | 2026-05-19 | 2026-10-30 | Digital Project Manager
| 13 | Live | UEA Shop EPOS System | Carry out ITCS support, to input into new UEA Shop tender process, checking security/compliance of the incoming system, or provide requirements for a separate electronic point of sale (EPOS) tender | Information not held - s.1(1)(a) | 2026-05-19 | 2027-04-30 | Digital Project Manager
| 14 | Live | eCommerce - Ticketing and Events | Embracing eCommerce to deliver smarter ticketing and events management, increasing revenue generation and lean systems operations across Sainsbury Centre, SportsPark/wider UEA opportunities | 2026/27 £48,800 2027/28 £49,297 | 2023-03-01 | 2026-10-30 | Digital Project Manager
| 15 | Live | CareerHub Re-procurement | Support and renew contract | 2026/27 £29,280 2027/28 £29,866 | 2026-05-20 | 2026-12-31 | Digital Project Manager
| 16 | Live | Timetable EventMAP API links | Provide new Application Programming Interfaces, allowing more efficient data transfers between UEA systems and 3rd Party (EventMap) software e.g. Exam, Timetabler, Booker | 2026/27 £44,338 2027/28 £45,668 | 2025-12-09 | 2026-12-31 | Digital Project Manager
| 17 | Live | CDP Voice & Telephony (upgrade) | Upgrade UEA telephony infrastructure, improving stability, security and integration with a Softphone solution to allow external calling both from Campus and Remote/Home Working | 2026/27 £111,770 2027/28 £120,000 | 2021-11-01 | 2026-09-30 | Digital Project Manager
| 18 | Live | Start of Year - Data, Systems and Enquiries [2026] | Cyclical Commitment - Continuous Programme of SOY procedures aligned to impacted systems and integtrated enquiry method | Information not held - s.1(1)(a) | 2026-02-05 | 2026-10-16 | Digital Project Manager
| 19 | Live | Confirmation and Clearing [2026] | Cyclical Commitment - Continuous Programme of Conf. and Clrng. procedures aligned to impacted systems and integtrated enquiry method | Information not held - s.1(1)(a) | 2026-02-09 | 2026-10-30 | Digital Project Manager
| 20 | Pipeline | Salesforce Migration to Education Cloud | Our current Salesforce org is on an older architectural platform. Salesforce new development is into cloud verticals on top of the base infrastructure. Working towards our digital resilience and cyber security goals, to a modern, secure and simple technology architecture. | s.43(2), Prejudice to commercial interests | 30/10/2026 (forecast) | Not yet live - no end date planned | Unallocated, no nominated Job Title of Officer Responsible for Delivery at time of response
| 21 | Pipeline | Maytas Cloud Migration | Maytas 5 is currently run as an on-premises service; however, Maytas 6 will be Cloud only based software, so UEA is required to upgrade supporting systems to allow for this transition. (Note simplified title - was "Maytas Cloud Migration from M5 to M6 SaaS") | 2026/7 = £64320.00 2027/8 = £64320.00 | 31/12/26 (forecast) | Not yet live - no end date planned | Unallocated, no nominated Job Title of Officer Responsible for Delivery at time of response
| 22 | Pipeline | SITS Feed to Website | Improve integration between SITS and Website, to eradicate repeated errors, mitigate increasing legal risk and improve recruitment/compliance | Nil, resource only | 31/12/26 (forecast) | Not yet live - no end date planned | Unallocated, no nominated Job Title of Officer Responsible for Delivery at time of response
| 23 | Pipeline | Automation of Assessment Mark Upload | Automate Assessment Mark upload files, to replace the current manual import regime and provide students with prompt/accurate feedback | Nil, resource only | 31/12/26 (forecast) | Not yet live - no end date planned | Unallocated, no nominated Job Title of Officer Responsible for Delivery at time of response
Question 1.
A list of ICT, digital, network, telephony or business-systems projects and programmes that are planned, approved or in progress for the financial years 2026/27 and 2027/28.
For each, please give the project name, a one-line description, the approved or estimated budget, the planned start and end dates and the job title of the officer responsible for delivering it.

## Q2
FOI_26-233 Appendix A
| Item No. | Status | Project Name | Name of External Supplier or Contractor, if already appointed
| 3 | Live | Data Centre Switch Replacement | Conscia Ltd
| 4 | Live | Network Control Core Switches and Automation Servers | Conscia Ltd
| 6 | Live | CDP Phase 1 – Building 3 Refurb (ITCS) | MACE, RLB Consultants
| 11 | Live | Migrate Apple Device Management to Intune | Moof IT, JAMF IT
| 14 | Live | eCommerce - Ticketing and Events | Maxica Consulting Ltd
| 17 | Live | CDP Voice & Telephony (upgrade) | Maintel
| 20 | Pipeline | Salesforce Migration to Education Cloud | Not a live Project at Report date, but will be "Salesforce"
Question 2.
Where a project in that list will be delivered with the help of an external supplier or contractor, the name of that supplier if one has already been appointed. If a published document already contains this information (for example a capital programme, an ICT or digital strategy or a forward plan), a link to it and the page reference is a complete answer and I would be grateful for it.